## Work Orders
WO # | Date received | Business | Customer | Phone | Site address | Job description | Priority | Status | Assigned to | Scheduled date | Hours logged | Materials cost | Amount invoiced | Paid? | Notes
WO-1001 | 2026-07-06 | Plumbing Co | Rivera Household | 555-0142 | 14 Oak St | Water heater replacement — no hot water | High | In progress | Sam T. | 2026-07-08 | 3.5 | 420 | 0 | No | Waiting on 50-gal tank delivery
WO-1002 | 2026-07-07 | HVAC Co | Cedar Property Mgmt | 555-0177 | 902 Cedar Blvd | Rooftop unit not cooling — annual service | Normal | Scheduled | Dana R. | 2026-07-10 | 0 | 0 | 0 | No | Access code at front desk
WO-1003 | 2026-07-05 | Electrical Co | Nguyen Residence | 555-0110 | 8 Pine Ave | Panel upgrade to 200A | Normal | Blocked | Alex P. | 2026-07-09 | 1 | 0 | 0 | No | Blocked: waiting on permit
WO-1004 | 2026-07-03 | Plumbing Co | Maple St Cafe | 555-0199 | 231 Maple Rd | Clogged main drain — emergency | Emergency | Done | Sam T. | 2026-07-03 | 2 | 85 | 340 | No | Invoice sent 2026-07-04
WO-1005 | 2026-06-28 | HVAC Co | Birch Ln Rentals | 555-0163 | 47 Birch Ln | Mini-split install — 2 zones | Normal | Paid | Dana R. | 2026-07-01 | 6.5 | 1250 | 2100 | Yes | Paid by card 2026-07-05

## How to use
Work order template — how to use it
Free from MasterBuilds (getmasterbuilds.com). Works in Excel, and in Google Sheets via File → Import.
Logging a job
1. Open the "Work Orders" sheet and add a new row under the examples.
2. Give it the next WO number (WO-1006, WO-1007, …) and the date the request came in.
3. Put which of your businesses it belongs to in the Business column (Plumbing Co, HVAC Co, Electrical Co — whatever you run).
4. Fill in the customer, phone, site address, and a short job description.
5. Set Priority and Status from the dropdowns, and note who it is assigned to.
6. As the job moves, update Status, log hours and costs, and record what you invoiced and whether it is paid.
What each status means
New — the request just landed and nobody has looked at it yet.
Triaged — you have reviewed it, set a priority, and confirmed it is a real job.
Scheduled — it has someone assigned and a date in the calendar.
In progress — work is happening now.
Blocked — the job cannot move. Write the reason in the Notes column (waiting on parts, a permit, or site access).
On hold — paused on purpose. Write the wake-up date in the Notes column so it does not get forgotten.
Done — the work is finished but not yet billed.
Invoiced — you have sent the invoice; record the amount in the Amount invoiced column.
Paid — the money is in. Set Paid? to Yes.
Priority
Low / Normal / High / Emergency — use Emergency for the no-heat, no-water, no-power calls that jump the queue.
Tracking more than one business
The Business column is what lets one spreadsheet hold several businesses at once.
Sort or filter by Business to see one company's jobs at a time, and keep separate running totals per business for your books.
Keep the customer's business separate from yours: Business is which of your companies did the work; Customer is who you did it for.
Tips
Never reuse a WO number — it is the one thing tying a job to its photos, texts, and invoice.
Keep the header row frozen (it already is) so it stays put as you scroll.
The Status, Priority, and Paid? columns are dropdowns — pick a value instead of typing, so a filter never misses a job to a typo.
When the spreadsheet stops scaling, this workflow is what MasterBuilds automates — getmasterbuilds.com